## Summary
Area Addressed | # Tasks Completed | # in Progress | Remaining to Address | Total Tasks | % Completed | Status
Immediate | 1 | 1 | 13 | 15 | 6.667% | Not Completed
Notifications | 0 | 0 | 7 | 7 | 0% | Not Completed
Records | 0 | 0 | 3 | 3 | 0% | Not Completed
Financial | 0 | 0 | 18 | 20 | 0% | Not Completed
All Closure Tasks |  |  |  |  | 2.222%

## Immediate Next Steps
Immediate Actions
Responsible Party | Description of Necessary Actions | Approx Date of Completion | Notes | Follow-up Actions | Completion Verified
Authorizer | Written Notice of Closure Draft and send letter of notification of closure to school's board. Cite relevant provisions of the charter or state/federal law as rationale for school closure. If closure is a decision by the school's board, obtain a copy of the board's resolution approving the closure. Send copies of closure notifications and board resolutions to Indiana Department of Education. |  |  |  | Yes
Authorizer Lead and Charter School Board Chair | Establish Transition Team and Assign Roles Team to include: • Lead person from Authorizing Staff • Charter School Board chair • Board contact for parent engagement • Lead board member for financial tasks • Lead board member for school admin task oversight |  |  |  | In Progress
Authorizer Lead and Charter School Board Chair | Talking Points Create talking points for parents, faculty, community, and press. Focus on communicating plans for orderly transition of students and staff. Distribute to transition team. |  |  |  | No
Authorizer Lead | Create “Charter School Closure: Frequently Asked Questions” Document General document from authorizer outlining authorizer’s policies, commitment to quality authorizing through supporting the transition of students to new settings, overview of transition steps, general timeline, checklist for parents transitioning to a new school, and authorizer contact information. |  |  |  | No
Authorizer Lead and Charter School Board | Initial Closure Notification Letter: Parents and School Distribute letter to faculty, staff, and parents outline: • Closure decision • Timeline for transition Copy must be given to Authorizer lead. |  |  |  | No
Authorizer Lead | Initial Notification to Local Public Schools All Indianapolis school districts and charter schools that offer the same grades offered in the school must be notified of the closing school’s closing and the potential for transfer of students. Copy must be given to Authorizer Lead. |  |  |  | No
Authorizer Lead and Charter School Board | Press Release(s)/Media Statements Authorizer (with feedback from transition team school representatives and school's board) draft press release. |  |  |  | No
Charter School Administrative Lead | Continue Current Instruction Continue instruction under current education program per charter contract until the end of school calendar for regular school |  |  |  | No
Charter School Administrator Lead | Secure Student Records Ensure all student records are organized, up to date, and maintained in a secure location. |  |  |  | No
Charter School Financial Lead | Secure Financial Records Ensure all financial records are organized, up to date, and maintained in a secure location. |  |  |  | No
Charter School Administrator Lead | Parent Contact Information • Student name • Address • Telephone • Email, if possible Copy must be given to Authorizer Lead. |  |  |  | No
Authorizer Lead, Charter School Administrator, and Charter School Parent Organization Leads | Convene Parent Closure Meeting • Make copies of “Closure FAQ” document available • Provide overview of authorizer closure policy and closure decision • Provide calendar of important dates for parents • Provide date for end of classes • Present timeline of transitioning students • Present timeline for closing down of school operations • Provide contact information for authorizer and school |  |  |  | No
Charter School Board Chair, Charter School Administrative Lead, and Charter School Faculty Lead | Convene Faculty/Staff Meeting Board Chair to communicate: • Commitment to continuing coherent school operations throughout closure transition • Plan to assist students and staff by making closing as smoothly as possible • Reasons for closure • Timeline for transition details • Compensation and benefits timeline |  |  |  | No
Charter School Board Chair | Maintenance of Location and Communication The school must maintain operational telephone service, maintain custody of business records, and maintain remaining assets until all business transactions are completed and legal obligations are satisfied. The school must immediately inform the authorizer if any change in location or contact information occurs. If necessary, a temporary base of operation should be established during the wind-up of the closing school’s affairs. |  |  |  | No
Charter School Board Chair and Charter Financial Lead | Insurance Policy The closing school must continue to have insurance coverage. The school’s asset and any assets that belong to others must be protected against theft, misappropriation, and deterioration. |  |  |  | No

## Notifications
Notifications
Responsible Party | Description of Necessary Actions | Approximate Completion Date | Notes | Follow-up Actions | Completion Verified
Charter School Board Chair and Charter School Administrator | Parent/Guardian Closure Transition Letter • Date of the last day of regular instruction • Cancellation of any planned summer school • Notification of mandatory enrollment under state law • Date(s) of any planned school choice fair(s) • Listing of the contact and enrollment information for charter,parochial, public, private schools in the area • Information on updating student records in pursuant to the state Freedom of Information Law before the end of classes • Advise the recipient to contact the school where the student intends to enroll and to have the new school contact the closing school to have the student’s educational records transferred • Contact information for questions and assistance Copy must be given to Authorizer Lead |  |  |  | No
Charter School Board Chair | Staff/Faculty Closure Transition Letter • Commitment of school’s board to transitioning staff • Commitment to positive transition for students into new educational settings • Timeline for compensation and benefits • Transition team member contact information Copy must be given to Authorizer Lead. |  |  |  | No
Charter School Board Chair and Charter School Financial Lead | Notification of Employees and Benefit Providers The school should establish an employee termination date and: • Notify all employees of termination of employment and contacts • Notify benefit providers of pending termination of all employees • Notify employees and providers of termination of all benefit programs • Terminate all programs as of the last date of service (health insurance; life insurance; dental plans; eyeglass plans; cafeteria plans; 401(k) and retirement plans; pension plans) Copy must be given to Authorizer Lead. |  |  |  | No
Charter School Finance Lead | Notification to Contractors Agreement The school must formulate a list of all contractors with contracts in effect, and: • Notify them regarding school closure and cessation of operations • Instruct contactors to make arrangements to remove any contractor property from the school by date certain (copy machines, water coolers, other rental property) • Retain records of past contracts as proof of full payment • Maintain telephone, gas, electric, water, insurance, Directors and Officers liability insurance long enough to cover the time period required for all necessary closure procedures to be complete Copy must be given to Authorizer Lead. |  |  |  | No
Charter School Financial Lead | Notification to Creditors Solicit from each creditor a final accounting of the school’s accrued and unpaid debt. Compare the figures provided with the school’s calculation of the debt and reconcile. Provide the Authorizer Lead with a written summary of this activity. |  |  |  | No
Charter School Financial Lead | Notification to Debtors Contact all debtors and demand payment. If collection efforts are unsuccessful, consider turning the debt over to a commercial debt collection agency. Provide the Authorizer lead with a written summary of this activity. |  |  |  | No
Lead board member for school admin oversight | Follow-Up Transfer A follow up procedure must be established to determine where each student enrolled at the time of closing will continue his or her education. Copy of this report must be given to Authorizer Lead. |  |  |  | No

## Records
Records
Responsible Party | Description of Necessary Actions | Approx Date of Completion | Notes | Follow-up Actions | Completion Verified
Charter School Board Chair | Disposition of Records Negotiate with appropriate legal entities to determine what body will be the final repository of the closing school’s records. Such entities might include the traditional public school district in which the charter school is located • All of the school’s business records and records relating to federal grants must be kept in accordance with 34 CFR 8042 • The final repository of all teacher records must retain a record of the teacher’s dates of employment with the school and what courses he or she taught while employed by the school • The final repository of all the closing school’s business records should maintain the records in accordance with Indiana Department of Education and Indiana Secretary of State |  |  |  | No
Charter School Administrative and Faculty Lead | Final Report Cards and Student Records Notice The school must ensure that: • All student records and report cards are completed and up to date • Parents/Guardians are provided with copies of final report cards and notice of where student records will be sent • Parents/Guardians receive a reminder letter or post card reminding them of the opportunity to access student records under the Freedom of Information Law Copy must be given to the Authorizer Lead. |  |  |  | No
Authorizer Lead and Charter School Board Chair | Transfer of Student Records As required by Indiana state statute, IC 20-33-2-10, the school must transfer all student records to the requesting school. • The final repository for all the closing school’s student records (that are not transferred to a student’s new school) must retain those records in accordance with the Indiana Department of Education’s Guidelines • In the event that students records have not been requested by another school, the student or the student’s family should be sent a notice by September 5th to the last known address of the student as soon as possible advising them where the records are located Submit a list of all students whose records have not been transferred to the Authorizer Lead. |  |  |  | No

## Finances
Financial
Responsible Party | Description of Necessary Actions | Approx Date of Completion | Notes | Follow-up Actions | Completion Verified
Charter School Financial Lead | Itemized Financials Review, prepare, and make available the following: - Fiscal year end financial statements - A cash analysis - A list of compiled bank statements for the year - A list of investments - A list of payables - A list of all unused checks (to collect and void) - A lit of any petty cash - A list of bank accountas (to close once all transactions have cleared) - A list of all payroll reports including taxes, retirements or adjustments on employee contracts |  |  |  | No
Charter School Financial Lead | U.S. Department of Education Filings File Federal Form 269 or 269a if the school was receiving funds directly from the United States Department of Education. 34 CFR 80.41. |  |  |  | No
Charter School Financial Lead | Final Tax Payments Determine taxes due and make final federal and state tax payments (every employer, including the school, which pays wages to employees is responsible for withholding, depositing, paying, and reporting federal income tax, social security taxes, and federal unemployment tax for such wage payments). |  |  |  | No
Charter School Financial Lead | Withholding Tax Return File the final withholding tax return. (Treasury Form 165) |  |  |  | No
Charter School Financial Lead | Final IRS Return File the final return with IRS. (Form 990 and Schedule A) |  |  |  | No
Charter School Financial Lead | PERF and TERF Make final payments into employee’s retirement funds |  |  |  | No
Charter School Financial Lead | Dissolution Forms and Reporting If applicable, the closing school should prepare to complete the 501(c)(3) dissolution process, including voting on dissolution, filing articles of dissolution, and sending notices to required state agencies (including DOR, Attorney General, and DWD). Resources and specific requirements can be found at <www.nolo.com/legal-encyclopedia/how-dissolve-nonprofit-corporation-indiana.html> |  |  |  | No
Charter School Financial Lead | Coordinating with Indiana Department of Education The closing school should coordinate with the Indiana Department of Education’s Charter School Liaison regarding procedural issues as well as satisfaction of financial issues related to state and federal funding. The full plan for winding-up and dissolution of the school should be shared with Department. |  |  |  | No
Charter School Financial Lead | Closeout State and Federal Grants A complete listing of state and federal grants received should be complied with State Board of Accounts audit. State grants must be closed out, including filling all final expenditures and performance reports. |  |  |  | No
Charter School Board Chair | Vendors The school must: • Create vendor list • Notify vendors of closure and cancel or non-renew agreements as appropriate |  |  |  | No
Charter School Board Chair and Charter School Financial Lead | Special Education If applicable, contact the Special Education director regarding accounting for, and close out of state and federal special education funds. |  |  |  | No
Charter School Board Chair and Charter School Financial Lead | Financial Statements and Fixed Asset Schedule The school must prepare a comprehensive fixed asset schedule and financial statements. The school must update this fixed asset schedule and financial statements quarterly until dissolution is complete. |  |  |  | No
Charter School Board Chair and Charter School Financial Lead | Asset Inventory and Creditor Determination The closing school’s assets should be inventoried and determination of any secured creditors made. |  |  |  | No
Charter School Board Chair and Charter School Financial Lead | Resolution of Dissolution and Plan of Distribution of Assets The school must adopt a resolution that the corporation be dissolved and that a plan of distribution of assets be implemented consistent with IC 20-5.5. • Assets obtained with federal funds, including Department of Agriculture Commodities, and equipment obtained through federal funds, including Department of Agriculture Commodities, and equipment obtained through the Special Education Cooperative should be distributed according to guidelines established by these entities • All assets should be distributed pursuant of the terms of the Charter Agreement |  |  |  | No
Charter School Board Chair and Charter School Financial Lead | Protection of Assets The school must protect assets against theft, misappropriation and deterioration. • This could mean moving the assets from the school to a safe storage facility • Insurance should be maintained on the assets until they are disposed of according to the plan of distribution |  |  |  | No
Charter School Board Chair and Charter School Financial Lead | Liquidation of Assets The school must liquidate assets in a manner that ensures the highest possible price is obtained. • This may be done by retaining and auctioneer • If an asset is subject to a security interest, the secured party should be contacted • No asset may be given away, except as authorized by law • Board members of closing school, their relatives, employees, and student s should not purchase any asset unless the purchase is disclosed to the closing school’s Board and the Charter School Board Chair and Charter School Financial Lead disclosure is made a matter of record in the Board’s official proceedings and approved by a majority of the non-interested directors |  |  |  | No
Charter School Board Chair and Charter School Financial Lead | Final Distribution of Assets All liabilities and obligations of the school must be paid and discharged (or adequate provision must be made therefore) to the extent of the closing school’s assets (IC 20-5.5). • Any assets held subject to written conditions or limitations must be disposed of in accordance with those conditions or limitations • Remaining assets must be assigned to a non-for-profit entity with an educational mission pursuant to the terms of the Charter Agreement (IC 20-5.5) |  |  |  | No
Charter School Board Chair and Charter School Financial Lead | Final Audit Obtain a final audit of the closing school’s financial affairs once close out and dissolution is complete. |  |  |  | No